## Bugs
Bug_ID | Title | Module | Severity | Priority | Steps to Reproduce | Expected | Actual | Status | Linked TC_ID | Notes
BUG-001 | Album placeholder links non-functional | Iframe/Album | Major | Medium | 1. Open Iframe page. 2. Switch into album iframe. 3. Click 'Follow on Twitter', 'Like on Facebook', 'Email me', 'Album', or any card's View/Edit. | Each link/button navigates to its target or performs its action. | All are href="#"; clicking does not navigate or perform any action. | Open | TC-033, TC-035 | Demo-site placeholders; logged as requirement-driven negative finding.
BUG-002 | PracticeForm hobby/city wiring bug | Practice form | Major | High | 1. Open practice form. 2. selectHobby() switched on gender values. 3. selectCity() opened the State dropdown. | selectHobby targets Sports/Reading/Music; selectCity opens the City dropdown. | selectHobby switched on Male/Female/Other; selectCity opened the State dropdown. | Closed | TC-058, TC-059 | Historical defect; FIXED by developer. Retained for traceability/history.
BUG-003 | Mobile-number length not validated | Practice form | Minor | Medium | 1. Open practice form. 2. Enter mobile '123' (under 10) or '12345678901' (over 10). 3. Submit. | Form rejects mobile numbers that are not exactly 10 digits. | TBD on run - verify whether short/long values are rejected; if accepted, this is a validation gap. | Open | TC-055, TC-056 | Watch item: confirm behavior during execution before final triage.
BUG-004 | Navbar links non-functional | Iframe/Album | Minor | Low | 1. Open Iframe page. 2. Switch into iframe. 3. Click navbar items. | Navbar links route to social/email/album destinations. | Navbar links are placeholders and do not route (subset of BUG-001 pattern). | Open | TC-033 | Inferred; consolidate with BUG-001 if treated as one defect.